			8/13	8/20	8/27	9/3	9/10	9/17	9/24	10/1	10/8	10/15	10/22	10/29	11/5
	Literature review—draft	August 27
	Literature review—final	September 15
3	Research plan—draft	August 13
	Research plan—complete	August 20
	Participant recruiting	August 27
	Observational research	September 17
	Interaction design	September 30
	Prototype	October 12
	Prototype evaluation	October 22
	Final report—draft	October 22
	Final report—complete	November 4