			8/13	8/20	8/27	9/3	9/10	9/17	9/24	10/1	10/8	10/15	10/22	10/29	11/5
3	Literature review—draft	August 27
	Literature review—final	September 15
3	Research plan—draft	August 13
3	Research plan—complete	August 20
	Participant recruiting	August 27
	Contextual interviews	September 17
	Interaction design	September 30
	Prototype	October 12
	Prototype evaluation	October 22
	Final report—draft	October 22
	Final report—complete	November 4